## Munka1
Date | Event | Discription | Hours
27. April | First online meeting | Discussion about the project and the participants | 1
1. June | First personal meeting | Meeting at Martin's office, discussion about the embedded board, collecting the board | 1
2. June | Studying the code | Investigating the previous team's code, learning their software architecture | 10
3. June | Setting up the environment | Downloading the virtual machine, understanding Quartus | 8
4. June | Online meeting | Introduction to all team members | 1
4. June | Patmos | Synthetizing patmos, creating build files, configuring the board | 8
8. June | Online meeting |  | 1
9. June | First steps with the board | Sending commands to the board, reading answers | 6
11. June | Online meeting |  | 1
11. June | I2C configuration | Reading and writing each register | 8
15. June | Basic functions | Setting up the basic functions of the embedded system (multithreading, LEDs, timers) | 10
16. June | Angles reading | Library created for reading the raw accelerometer sensor data | 8
17. June | Collecting the drone | Collecting the drone from other student, investigating the assembly, issues with the drone's board | 6
18. June | Online meeting |  | 1
18. June | Changing boards | The drone's board and the other one were not working the same way. We swapped them so we could flash the drone's program. | 8
21. June | Angles calculation | Calculating the orientation from accelerometer data using trigonometrical formulas. It is noisy and inaccurate | 8
22. June | Motor control | Writing the code to directly access and control the motors. Testing them at lab | 10
23. June | Introducing PID controller | Basic 1 level PID controller has been introduced based on the calculated angles. | 8
25. June | Online meeting |  | 1
29. June | New angle calculation | Angle is calculated based on accelerometer and gyro data using complementary filtering. Angle seems more accurate. | 8
2. July | Online meeting |  | 1
4. July | First flight test | After collecting the blades, flight tests could be performed at ASTA. | 8
7. July | Remote controller | Library created for reading the remote controller's signals, now we can change the PID values remotely. More flight tests | 8
10. July | Start of vacation
5. August | End of vacation
10. August | Yaw controller | Introducing yaw controller to eliminate spinning. More tests, PID tuning. | 8
12. August | 2 level PID | Introducing 2 level PID controller: 1 for angle position, 1 for angle velocity. More flight tests, tuning parameters. The drone is flying more stable now, but still not ok. | 8
13. August | Flight tests | Performing flight tests, tuning PID values. Trying different angle calculation and filtering methods. | 8
17. August | Flight tests | Performing flight tests, tuning PID values. Not so much success, the drone still flips in the air. | 8
19. August | Filtering sensor data | The drone performs random flips during flight. Plotting the sensor data to find the root of the problem. Filter applied | 8
20. August | Online meeting |  | 1
20. August | Repairing | The sensors are damaged after an unfortunate landing. Swapping them with the sensors from the other board. Ordering new blades. 3D printing new case. | 8
26. August | Telemetry module | Creating telemetry library to plot the sensor values real-time during flight. Fixed-point values introduced. | 8
27. August | Online meeting |  | 1
27. August | Investigating noise | The sensors show random peaks. After filtering it is still an issue, it makes the flight unstable. | 7
2. Sept | Filtering outliers in sensor data | The previous random noise problem is solved by outlier cancellation. Flight is more reliable now.
9. Sept | 3D printing battery holder | To ensure the fixed mass distribution we had to hold the battery in place. A 3D printed component solved this problem. | 4
10. Sept | Removing interrupts | Interrupts have been replaced by timed loops. Worst case execution time is measurable now. | 4
16. Sept | Optimizing execution time | We had to reduce the cycle time from 15 to 4-5 ms. We did it by introducing look-up table instead of trigonometric calculations. | 4
17. Sept | Finalize fixed-point structure | Replacing floating-point calculations with fixed-point. | 4
24. Sept | Remote PID interface | We created a remote interface to tune the PID values in run-time (without reprogramming the board). | 4
25. Sept | Documentation |  | 4
|  |  | Spent hours: | 219